## Gantt Chart
Project Title: Modern way to Store Data
Chase Bank
James Smith |  | PROJECT START: | 2023-01-03
|  | Display Week: | 1 |  | 2023-01-16 |  |  |  |  | 2023-02-13 |  |  |  | 2023-03-13 |  |  |  | 2023-04-10 |  |  |  | 2023-05-08 |  |  |  | 2023-06-05 |  |  |  | 2023-07-03 |  |  |  | 2023-07-31 |  |  |  | 2023-08-28 |  |  |  | 2023-09-25 |  |  |  | 2023-10-23 |  |  |  | 2023-11-20 |  |  |  | 2023-12-18
[5 empty] | 2023-01-16 |  |  |  |  | 2023-02-13 |  |  |  | 2023-03-13 |  |  |  | 2023-04-10 |  |  |  | 2023-05-08 |  |  |  | 2023-06-05 |  |  |  | 2023-07-03 |  |  |  | 2023-07-31 |  |  |  | 2023-08-28 |  |  |  | 2023-09-25 |  |  |  | 2023-10-23 |  |  |  | 2023-11-20 |  |  |  | 2023-12-18
TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2023-01-02 to 2024-01-01
1 Project Initiation
1.1 objectives and scope |  | 50% | 2023-01-03 | 2023-01-10
1.2 Check Stakeholders |  | 100% | 2023-01-12 | 2023-01-19
1.3 initial preliminary research |  | 100% | 2023-01-19 | 2023-01-26
1.4 milestones and deliverables |  | 100% | 2023-01-26 | 2023-02-02 | bar: 2023-01-30
2 Gathering Requirements and Selecting Solution
2.1 Check current data Storage and Performance Requirement |  | 15% | 2023-02-03 | 2023-02-07
2.2 Security and Compliance requirements |  | 100% | 2023-02-08 | 2023-02-14
2.3 Assess compatibility with existing systems |  | 45% | 2023-02-14 | 2023-02-21
2.4 Selecting Best Solution |  | 100% | 2023-02-22 | 2023-03-01
3 System Design and Architecture
3.1 Establish the overall system architecture |  | 10% | 2023-03-02 | 2023-03-10
3.2 Design data models and schemas |  | 100% | 2023-03-10 | 2023-03-17
3.3 data integration and migration |  | 50% | 2023-03-17 | 2023-03-24
3.4 Plan backup, disaster recovery, and data retention |  | 50% | 2023-03-24 | 2023-03-31 | bar: 2023-03-27
4 Development, Deployment and Rollout
4.1 Create or customize storage solution |  | 40% | 2023-04-03 | 2023-06-22
4.2 Sync with current banking software and data migration techniques |  | 30% | 2023-06-23 | 2023-07-13
4.3 Create a plan for a pilot deployment, and carry it out in a safe environment |  | 100% | 2023-07-14 | 2023-07-21
4.4 Install the new system in production and Monitoring |  | 80% | 2023-07-17 | 2023-07-27 | bar: 2023-07-24
5 Training, Documentation, Review, and Maintenance
5.1 Develop training materials and provide guidance |  | 60% | 2023-07-31 | 2023-08-21
5.2 Documentation and Knowledge Transfer |  | 40% | 2023-08-21 | 2023-08-28
5.3 Evaluating and checking for Improvements |  | 35% | 2023-08-21 | 2023-10-05
5.4 Maintenance and Performance Monitoring |  | 30% | 2023-10-05 | 2023-10-31 | bar: 2023-10-30

## Salary
Role | Total Hours | Hourly Rate ($) | Total Cost ($)
Project Manager | 250 | 75 | 18750
Senior Software Engineer | 500 | 90 | 45000
Junior Developer 1 | 1000 | 40 | 40000
Junior Developer 2 | 1000 | 40 | 40000
Junior Developer 3 | 500 | 40 | 20000
Subject-Matter Expert | 100 | 200 | 20000
Total | 3350 |  | 183750

## Total Budget
Project Budget
Months | Cumulative cost | Planned | Actual | Total Budget
January | 15000 | 15000 | 15000 | 490000
February | 55000 | 40000 | 30000 | 490000
March | 95000 | 40000 | 35000 | 490000
April | 145000 | 50000 | 45000 | 490000
May | 195000 | 50000 | 45000 | 490000
June | 255000 | 60000 | 60000 | 490000
July | 315000 | 60000 | 60000 | 490000
August | 375000 | 60000 | 50000 | 490000
September | 425000 | 50000 | 30000 | 490000
October | 450000 | 25000 | 20000 | 490000
November | 460000 | 10000 | 10000 | 490000
December | 470000 | 10000 | 10000 | 490000
total |  | 470000 | 410000

## Tasks&sub-Tasks
ID | TASK NAME | DUE DATE | MILESTONES | MILESTONE DUE DATE
mm-dd-yyyy
1 | Project Initiation |  | Approved Project Charter | 2023-02-02
1.1 | objectives and scope | 2023-10-01
1.2 | Check Stakeholders | 01-19-2023
1.3 | initial preliminary research | 01-26-2023
1.4 | milestones and deliverables | 2023-02-02
2 | Gathering Requirements and Selecting Solution | 2023-01-03
2.1 | Check current data Storage and Performance Requirement | 2023-07-02 | Selecting Best Solution | 2023-01-03
2.2 | Security and Compliance requirements | 02-14-2023
2.3 | Assess compatibility with existing systems | 02-21-2023
2.4 | Selecting Best Solution | 2023-01-03
3 | System Design and Architecture | 03-31-2023
3.1 | Establish the overall system architecture | 2023-10-03 | completion of architecture and design | 03-31-2023
3.2 | Design data models and schemas | 03-17-2023
3.3 | data integration and migration | 03-24-2023
3.4 | Plan backup, disaster recovery, and data retention | 03-31-2023
4 | Development, Deployment and Rollout | 07-27-2023
4.1 | Create or customize storage solution | 06-22-2023 | Completion of Deployment | 07-27-2023
4.2 | Sync with current banking software and data migration techniques | 07-13-2023
4.3 | Create a plan for a pilot deployment, and carry it out in a safe environment | 07-21-2023
4.4 | Install the new system in production and Monitoring | 07-27-2023
5 | Training, Documentation, Review, and Maintenance | 10-31-2023 | Project Completion | 10-31-2023
5.1 | Develop training materials and provide guidance | 08-21-2023
5.2 | Documentation and Knowledge Transfer | 08-28-2023
5.3 | Evaluating and checking for Improvements | 2023-05-10
5.4 | Maintenance and Performance Monitoring | 10-31-2023